## Slide 1: As-Builts Final Gate Review March 11 2013
<number>
Notes: <number>

## Slide 2
Define
Measure
Analyze
Improve
Control
Create
Project
Definition
Map the process
Capture customer requirements
Validate
Measurement
System for output Y
Collect data
Establish
Baseline
Capability
Identify potential sources of
variation and Waste
Analyse root causes
Establish potential process improvements
Prioritise key X’s - process inputs
Implement control plan
Document
Process.
Implement
Controls
Determine Final
Process Capability
D M A I C Roadmap
Identify
Solution
Plan
Improvements
Validate
Solution
Implement
Improvements
Gate review
Gate review
Gate review
31 July
18 June
15 Oct
Monitor Project Performance
Over Time
11 March

## Slide 3: As–Builts Project Team.
Project Sponsor : Mike Maunsell
Business Sponsor : Steve Tobin
Process Owner: Kevin Normanton
Draughting Manager: Shane Ballantyne.
Project Leader : Rod Pedersen
Team members:
  Build Manager : Michael Walding
  Draughting Technician : Truby Morgan
  Change Management: Katherine Faire
  Senior Draughtsperson Paul Dickons
DEFINE

## Slide 4: Voice of the customer
Shane Ballantyne
  I want my team to complete their work without having to deal with poor quality as – builts
  Steady delivery of accurate records to draughting team in a timely manner.
  Consistent reliable as-built information to free up our time.
Kevin Normanton
  As-Builts ,right first time every time from the sub-contractors and better visibility of progress in the field.
Mike Maunsell.
  The as-builts are crucial in enabling us to invoice chorus and reduce our WIP.
  This project has been identified from our strategy weekend as being high priority and needs a consensus approach to deliver real improvement in bottom line results.
DEFINE

## Slide 5: Problem and Objective
What is an As-Built ?
  A field recording, documenting actual build location and specifications of all plant installed on the project (BAU or UFB).
What is the problem :
  Tracking of as-built records is not visible. There is a general lack of accountability for doing as-builts to the right standard and quality. Also poor understanding and accuracy affects the timely completion of As-builts to the Draughting team.
Project Objective
  To improve the quality and accuracy of the as- builts.
  To Improve the tracking and visibility of as- builts
  To reduce the time taken to complete the as-builts and deliver the as-builts to the draughting team within the required timeframe.
Project metrics include:
  # of rejections from the draughting team.
  # of As-builts delivered daily to draughting team
  Time taken to produce as-builts (mhrs) and lead time.
  WIP figure waiting for as-builts
  Visibility and tracking metrics (daily management of process )
DEFINE

## Slide 6: Data: As-Builts. Quality and time
Summary: The average quality of the as-builts delivered to the records team is 6.3.
The average time taken to submit as-builts to records team is 14 days after cabinet completion
Average Quality score = 6.3
Average time as-builts are delivered after cabinet completion= 14 days
The quality target is 9.
The delivery target is 2 days
28 days after is a problem.
Measure / Analyse
“You can’t improve a process if you can’t measure it.”
Deming

## Slide 7: Data: As-Builts Quality
Summary: Average score of 6.3 /10.
Focus areas for improvement are :
By Area: Dunedin, Ashburton and Wellington.
By Type: Civils and Hauling As-Builts .
Measure/Analyse

## Slide 8
Top 9 “causes” from fishbone diagram.
Design changes
No defined delivery process
Tracking of as-builts
Multiple contractors shifting responsibilities.
The number of contractors in the cabinet area
The number of rejections due to poor quality
Lack of training or skills required to do as-builts
Not enough field recording draughties to do QA in the field
As-Builts SOPs not readily available or confusing
Measure/Analyse

## Slide 10: Change Management Strategy
Measure/Analyse

## Slide 11: Change messages from the sponsor
Measure/analyse
Steve Tobin has my full delegated authority. If there is doubt or conflict, Steve has the final say.
EVERYONE has a role to play in making the project successful - whether that is active participation or support of the processes.
As-builts are one of our top priority projects. We all agreed this at the May strategy session.
I’m committed to this path for the as-builts and I need your support.
This is a new approach for the project, for Downer and for most of us personally. It’s our first time using the continuous improvement methodology of Lean Six Sigma.
This is a fantastic opportunity for all of us to build a better as-built process and to learn about continuous improvement.

## Slide 12
 | As-Builts list of Potential Process Improvements | To do | Impact
1 | Create the delivery process to records. For each cabinet include start and finish dates. | Easy | High
2 | Provide faster feedback for poor quality as-builts. (QA at point of delivery ) | Easy | High
3 | NCRs raised and registered for poor quality as builts | Easy | High
4 | Communicate end to end as-builts process for cabinet build to all sub-contractors | Easy | Med
5 | Develop Comms plan to as-builders to lift awareness and enforce compliance | Easy | Med
6 | All sub-cons to have contracts with Downer that specifically include as-builts | Easy | Low
7 | Improve design to reduce changes in the field | Easy | Low
8 | Include as-built stds in job pack issued to sub-cons | Med | Med
9 | PMs to own the performance relationship with sub-cons and provide 1:1 feedback | Med | Med
10 | Develop a new tracking /measuring system for as-builts | Hard | High
11 | Define as-builts stds and check sub-con skills /capability against the stds | Hard | High
12 | Clear consequences for poor quality as-builts performance and reward good quality | Hard | High
13 | Develop a list of approved as-builders that are trained and qualified. We will only accept as-builts from approved as-builders | Hard | High
14 | Develop leadership capability to ensure problems are not passed on particularly for as-builts. | Hard | High
Improve/ Control

## Slide 13: Improvements Implemented
UFB recording guidelines rewritten / simplified 25 pages to 16.
New guidelines flipchart checklist designed and printed (120copies )
Nominated as-builders trained and mentored. (Wgtn and LNI )
A3 base plan layouts defined and implemented.
Progressive checking by build zone for each cabinet (cover sheet)
Build manager accountability + improved capability.
Frixion black Erasable ink pens used to draw as-builts on base plans.
New process map
Status report from Draughting team.
Photo of cabinet installation with each as-built.
Improve/control

## Slide 14: Results potential and actual
Good levels of engagement from the sub-contractor, build and draughting teams.
25% reduction in draughty processing time (40hrs per cabinet )
  40 x 350 cabinets = 14000.00 mhrs x 33 per hr $462,000.00
Reduction in amount of rework. Avg of 3.8 queries per cabinet.
  80 mhrs per week reduced collating and fixing as-builts in the wgtn Build teams. = 4160.00 mhrs per year = $137,280.00 x 3 areas = $411,840.00.
Total estimated hard savings from this project will be $873,840.00 (conservative)
Improved quality and delivery. Reduced volume of as-builts from average of 70 sheets to 14. (standard format)
As-builts submitted on average 2.25 days after build complete date (8 cabinets measured) compared to average of 14 days.
Improve/ Control

## Slide 15: Feedback
Hi Michael,
Feed back for the recordings PRO/AU FFP13:
In general, since this is my first recordings from Daniel Renshaw Drainage, I can rate the recordings 7.5 out of 10 compared to other recordings I have worked with.
Cheers, Jesse Respecio Draughtsperson Downer
Hi Paul
I have all done with WN/BN 101 As-built. Please tell the drawer of the as built: well done, that’s the best as built I have ever got.
As far as I am concerned, all the things that I ever want to find in an as built, clarity, tidiness, sufficient dimension, are achieved in this as built.
Cheers Mintie
Hi Rod,
As discussed yesterday to demonstrate the improvement that the new as-built process is achieving in the quality of the as-built records I have compared three Petone Year 2 cabinets.
PTN FFP5 as-builts were produced under the old process and resulted in 47 separate queries back to the build team for more detail or information.
PTN FFP24 and FFP14 as-builts were produced using the new ‘base plan supplied’ format and resulted in an average of 12 separate queries back to the build team for more detail or information.
Cabinet FFP5 took 50% more time to complete the records update work than the average of the other two cabinets.
It looks like that the evidence is pointing to what we are hearing anecdotally that the new methodology for producing civil as-builts is improving the quality of the as-builts and reducing the time it is taking for the records team to complete their work. I would suggest that once the new QA component of the process kicks in fully the 12 queries per cabinet on the ‘new process’ cabinets should be able to be reduced significantly.
Hope that helps. Shane

## Slide 16: Control Plan

## Slide 17: Lessons learnt / Pitfalls to avoid
This project has been open to long and should have been closed Dec 2012.(increased speed for next time)
Take up has been slow outside of Wellington.
  Note: for next LSS project wider stakeholder representation required from other geo areas.
Measurement/tracking system for as-builts still not fully operational as yet.
Built some capability and trust with the approach and the roadmaps.
Overall results are starting to turn positive.
Needs a push by PMs to carry on the work and bed in the change.
Risk of this project being half implemented in some areas due to perception that current method is ok .
Dollar savings are there for the taking but are est. at this stage apart from wellington.

## Slide 18: Final Gate Review
Criteria
for Go, Cancel, or Recycle decision
For all Gate Reviews Consider
People Factors
Financial Analysis (Business Case)
Risk Assessment/ Management
Voice of the Customer (VOC)
Project Documentation / Materials
Lessons Learned
Key Questions to Consider
Have the improvements been implemented and the targets met?
Has the improved process been accepted by the team?
Has the project been transitioned to the process owner?
Completion of Control phase
Final Gate
Control plan
Visual controls
Control charts
Target improvements met – process is stable
Control plan in place